## Slide 1
REPORTING OF ACTIVITIES
Implementation Seminar

## Slide 2
Content
Overview
Reports
Describe the progress
Deviations
Supporting documents
Closure

## Slide 3
Challenge
Idea
Project implementation
Outputs
Results
OVERVIEW
CHANGE

## Slide 4
Project partner report
Consolidated progress report
Final report
REPORTS

## Slide 5
What will JS look for ?
DESCRIBE THE PROGRESS
Are you on track?
Progress towards main outputs?
Main activities undertaken?
Main parties involved?
Any travels outside EU and Programme area?
Any major events you attended? What was achieved?
Do activities justify expenditure?

## Slide 6
Advices:
Go straight to the point
Describe progress towards delivering outputs, implementing activities
Mention if any draft/test versions of outputs are ready
Describe problems/deviations and solutions found
DESCRIBE THE PROGRESS

## Slide 7
Advices:
Clear descriptions and explanations
Provide realistic data that is supported documentally
Provide additional information that you would like JS/MA to know
Report is a basis for regular payments and monitoring of project’s progress
DESCRIBE THE PROGRESS
REMEMBER!

## Slide 8
What is the level of flexibility?
DEVIATIONS
A must: consult with your JS Manager
CHANGE PROCEDURE
MINOR CHANGES
MAJOR CHANGES
Describe in REPORT
Please refer to presentation “Project changes”

## Slide 9
All of the project partners have to secure audit trail when implementing project activities from the very beginning of the project implementation.
Evidence of the implemented activities must be enclosed in eMS.
SUPPORTING DOCUMENTS
Lists of participants, photos from events, all related materials (invitations, agendas, hand-outs, etc.) of the event must be presented for reporting purposes, and originals saved by the PP for auditing and control purposes.

## Slide 10
CLOSURE
FULLY IMPLEMENTED
Project overall objective
Project specific objectives
Project main outputs
Project activities
When to report on output? Only when final version delivered!
DURABILITY must be ensured

## Slide 11
Report usually takes more time than you planned.
Keep the daily paperwork in order (time-sheets, photos)
You report to Financial Control and Joint Secretariat.
FC and JS will have many questions, be responsive.
The speed how quickly you receive payments depends on PPs, FC, LP, JS and MA.
USEFUL TIPS