## Slide 1: Project lifecycle
25 April 2018

## Slide 2: TIME FRAMES AND CONTRACTS
Please note:
All relevant information about project implementation (contract / agreement templates / communication package and etc.) in the website: www.latlit.eu
Updated Programme manual – published on 26th April, 2018.
As PPs are obliged to keep and provide all the required information on Project implementation (including natural person data) to the Programme, partners must ensure processing and movement of such data with the requirements set in Regulation (EU) 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regard to the processing of personal data and on the free movement of such data and repealing Directive 95/46/EC (General Data Protection Regulation).

## Slide 3: PROJECT HAND OVER IN eMS
Guidance how to implement the project via eMS (part I) section 5
Lead applicant shall enter section “Lead Partner” on the left side menu
write the username of the prospective LP (and press button “Declare as Lead partner”
The JS shall approve proposed LP.
When the LP is accepted by the JS, the project state will be changed to “Startup”.
User needs to be already registered in the eMS
*e-mail of Lead Partner user in eMS shall match the Lead Partner contact person

## Slide 4: TIME FRAMES AND CONTRACTS
Contracting
(Up to 2-3 months)
Implementation
(Up to 24 months)
Closure
(3 months)
Post Project
(5 years after final payment)
MC approval date
Project start date
Project end date
Final payment

## Slide 5: TIME FRAMES AND CONTRACTS
Project start:
Subsidy Contract (between MA and LP)
Partnership Agreement before submission of 1st Project Report (between LP and PPs)
Establishment of project management structure
Kick-off meeting (if relevant) (LP, PPs, stakeholders, MA/JS)

## Slide 6: SUBSIDY CONTRACT
Start and end dates of the project are stated in Preamble
Total eligible budget in maximum, project budget can not be increased (§ 2, Point 1)
All exchange of information in the eMS (§ 4)
Payments are done on the basis of the validated total eligible expenditure only (§ 2, Point 4)
No advance payments (§ 5)

## Slide 7: SUBSIDY CONTRACT
Lead partner (LP)
bears the overall financial and legal responsibility for the project and for the PPs
all communication with Programme bodies (MA/JS, etc.) via LP
Responsible for:
signing of the partnership agreement
overall project management and establishment of reliable project monitoring system
requesting necessary project changes, if any
preparing consolidated project reports for requesting payments of spent ERDF funding
timely preparation of partner reports
Respecting Programme rules
Project partner (PP)
Responsible for:
implementation of all the project activities assigned
management of its part of the project
respecting Programme rules
guaranteing sound financial management of its budget
providing proofs of the project progress
informing the LP on the problems, on necessary changes in the project
Lead Partner
Project Partner
Project Partner
Project Partner

## Slide 8: SUBSIDY CONTRACT
Payments
The LP shall transfer the received ERDF co-financing to the PPs within maximum one month in full and shall upload proof to the eMS within 5 (five) working days after the transfer is made to each partner (§ 5, Point 11)
Payments to the LP will be made on a reimbursement basis and no advance payments are available from the ERDF funds of the Programme (§ 5, Point 2)
If any expenditure is considered ineligible by the MA, the MA has a right to deduct an unduly paid amount from the payment of ERDF co-financing to the Project or start the recovery procedure (§ 13, Point 1 and Point 2). In such a case, the PP has to repay to the LP their respective amounts unduly paid.

## Slide 9: NATIONAL CO-FINANCING
UP TO 5% OF TOTAL PARTNERS’ BUDGET
For more information contact:
Irina Brasle irina.brasle@varam.gov.lv; 67026462
Information available on webpage
http://www.varam.gov.lv/lat/fondi/ets_1420/?doc=16884
Main regulation
Ministru kabineta 2015.gada 22.aprīļa noteikumi Nr.200 “Valsts budžeta līdzekļu piešķiršanas kārtība Eiropas Strukturālo un investīciju fondu mērķa “Eiropas teritoriālā sadarbība” programmu finansējuma saņēmējiem no Latvijas”
DEADLINE: within 3 months after signing SC and PA.

## Slide 10: NATIONAL CO-FINANCING
UP TO 7,5% OF TOTAL PARTNERS’ BUDGET
For more information contact:
Renata Stambrauskė renata.stambrauske@vrm.lt; 852 718478
Main regulations
Lietuvos Respublikos Vyriausybės 2015 m. gegužės 27 d. nutarimas Nr. 520
Lietuvos Respublikos valstybės biudžeto lėšų, skirtų 2014-2020 metų Europos teritorinio bendradarbiavimo tikslo programoms bendrai finansuoti, naudojimo taisyklės
Information available on webpage
http://latlit.eu/how-to-implement/
National co-financing for Lithuanian partners
DEADLINE: within 12 months after signing SC.

## Slide 11: TO DO LIST AT PROJECT START
  Organise kick-off meeting (if relevant) or communication via phone/skype with all partners at project start
  Discuss and prepare detailed project plan
  Send out press releases in national languages
  Place posters at each PP location
  Sign Partnership agreement

## Slide 12: IMPLEMENTATION
  Start as fast as possible: projects usually delay
  Implemented in line with Application Form
  Realistic time planning (e.g. public procurement procedures)
  Follow reporting schedule: reporting takes more time than planned
If you have questions:
  read Programme manual
  ask your JS manager

## Slide 13: IMPLEMENTATION
  Ensure sufficient human resources
  Good project manager and financial manager – part of project success
  Efficient communication within Project
  Clear division of activities and budget between PPs

## Slide 14: FINANCIAL CONTROL
IN LATVIA – CENTRALISED
No costs foreseen in the partners’ budget
Contact details on the web
Inform your controllers
Ask for requirements
For more information
http://latlit.eu/how-to-implement/ Financial control in Latvia
IN LITHUANIA – DECENTRALISED
Costs should be foreseen in the partners’ budget
Run procurement
Get approval from Ministry of Interior
Sign the contract
Inform LP
FC shall apply for access in eMS
For more information
http://latlit.eu/how-to-implement/
Financial control in Lithuania

## Slide 15: CHANGES IN THE PROJECT
Types of changes:
Minor changes communicated via Consolidated progress report
Minor changes requested by Modification request in eMS
Major changes requested by Modification request in eMS
Use the word form for preparation of Request for changes and harmonise it with JS before submission in eMS http://latlit.eu/how-to-implement/reporting
Write in the Request for changes:
WHAT WAS PLANNED
WHAT YOU WANT TO CHANGE (Workplan & Budget)
WHY
WHAT IS THE IMPACT ON PROJECT
READ PROGRAMME MANUAL 7.2 PROJECT CHANGES

## Slide 16: REPORTING & PAYMENTS
To assess if the project is on track, regular reporting has to be ensured on:
Implemented activities and on achievement of the project main outputs and results
Finances
PARTNER REPORT
each Project partner and
Lead partner
verified by Financial Control
CONSOLIDATED PROGRESS REPORT
Prepared only by Lead partner
Reporting periods are specified in eMS / Application from

## Slide 17: REPORTING & PAYMENTS
Partner reports
Up to 2 months
Certification by FC
2 weeks
Consolidated progress report
MA makes 70% ERDF payment to LP
Up to 2,5 months
MA makes 30% ERDF payment to LP
2 weeks
End of reporting period
2 weeks
LP transfers shares of ERDF funding to PPs
LP transfers shares of ERDF funding to PPs
1 month
1 month

## Slide 18: SUPPORT BY MA / JS
Information on website (e.g. contract / agreement templates, State aid documents, communication package)
Advice to projects and consultations (e.g. via email / phone / in the office in Riga or Vilnius)
Seminars: implementation, communication, reporting, procurement
Project visits (e.g. on-spot and to kick-off / management meetings)

## Slide 19: PROJECT CLOSURE
Steps to be taken:
Plan closure
  − Resources
  − Timing
  − Last reimbursement
Finalise all project activities
Communicate all results
Accumulate project records
Prepare final report
BE AWARE !
All outputs co-financed by the Programme must comply with the applicable Programme information and communication requirements
The ownership of the project outputs (infrastructure and/or productive investments, produced during the project implementation) must remain with the LP or project partners;
The LP and project partners must assign a contact person for 5 years after the final payment of the ERDF co-financing has been made to the LP from the Programme.

## Slide 20: PROJECT CLOSURE
Obligations after project closure
Ownership of project outputs – not allowed to transfer ownership, titles, industrial and intellectual property rights for outputs of the project related to investment in infrastructure and/or productive investment during the project duration and at least five years (or in some cases ten years) after the final payment to the project has been made
Retention of documents – at least for five years after the final payment has been made by the MA to the LP
Irregularities found after project closure

## Slide 21: PROJECT CLOSURE
Project legacy
Ensuring that project activities have a lasting impact on project partner organisations and stakeholders
Ensuring that project activities have a lasting impact on the wider programme area and beyond
Trying to ensure that there is commitment and funding to take the next steps

## Slide 22: Thank you! Paldies! Ačiū!
Notes: Thank you all!